## Sheet1
S.No | Task | Priority | Status | Start Date | End Date | Comments
1 | Abou us and contact page | Low | Completed | 2025-07-14 | 2025-07-14
2 | News page implementaions | Medium | Not Started
3 | Tools | Medium | Not Started
4 | DRF implementaions | Low | Completed | 13-07-2025 | 13-07-2025
5 | Jwt token implementations | Low | Completed | 13-07-2025 | 13-07-2025
6 | Snippet implementaions | Low | Not Started
7 | Privacy policy, terms and condition | Low | Completed | 16-07-2025 | 16-07-2025
8 | Wright us form | Low | Completed | 16-07-2025 | 16-07-2025
9 | Subcriber Newletter form | Low | Not Started
10 | Send Message form | Low | Completed | 17-07-2025 | 17-07-2025
11 | Django Admin Filters | Low | In Progress | 17-07-2025 |  | This is for wright for us, send message, subscribers.